## Details
Cart Management Estimation
Estimates are shown as Low, Most Likely, and High man-days. Product/cart options are excluded.
# | Area | Task | Scope / Deliverable | Low | Most Likely | High | Depends On | Notes
1 | Database | Finalize ERD & table fields | Validate cart/cart_item fields, nullable customer/user ownership, branch relation, statuses, source. | 0.5 | 0.5 | 1 | - | Based on provided ERD image.
2 | Database | Indexes & constraints | Indexes for active cart lookup, FK indexes, quantity checks, and required constraints. | 0.5 | 0.5 | 1 | - | Exact uniqueness depends on business rule for one open cart.
3 | Backend | Entities/DTOs/repositories | Cart and cart item models, DTOs, mapping, repository queries. | 1 | 1.5 | 2 | Database
4 | Backend | Add to cart API | Create/open cart, add product, merge existing line, validate branch/product availability, recalculate totals. | 1 | 1.5 | 2 | DTOs
5 | Backend | Modify cart API | Modify item details/notes and cart metadata where allowed. | 0.5 | 1 | 1.5 | Add to cart
6 | Backend | Update quantities API | Set/increase/decrease quantities, prevent invalid zero/negative handling, recalculate totals. | 0.5 | 1 | 1.5 | Add to cart
7 | Backend | Remove item from cart API | Remove one line, recalculate totals, close/delete empty cart rule. | 0.5 | 0.5 | 1 | Add to cart
8 | Backend | View cart API | Return cart header, items, totals, product summary, status/source. | 0.5 | 0.5 | 1 | DTOs
9 | Backend | Clear cart API | Clear all items or mark cart cleared/cancelled; audit changes. | 0.5 | 0.5 | 1 | View cart
10 | Backend | Checkout API | Validate cart, lock/recheck totals, create/prepare order request, mark cart checked out. | 1.5 | 2 | 3 | All cart APIs | Order/payment/inventory flows excluded unless already existing.
11 | Backend | Validation & error handling | Standardize validations, status transitions, not-found/branch-closed/product unavailable responses. | 0.5 | 1 | 1.5 | All APIs
12 | Backend | Concurrency handling | Protect quantity updates and checkout from duplicate/parallel requests. | 0.5 | 1 | 1.5 | All APIs | Important for add/update/checkout race conditions.
13 | Testing | Unit tests | Service-level tests for add, update, remove, clear, totals, invalid cases. | 1 | 1.5 | 2 | Backend
14 | Testing | Integration/API tests | Controller/API tests with DB, checkout happy/error paths. | 1 | 1.5 | 2 | Backend
15 | Documentation | Postman/API collection | Document endpoints, requests/responses, status codes, sample flows. | 0.5 | 0.5 | 1 | APIs
16 | Documentation | Developer handover notes | Short README for DB assumptions, business rules, extension points. | 0.5 | 0.5 | 1 | All
17 | Review | Review & rework | Code review fixes, small requirement clarifications, cleanup. | 2 | 3 | 5 | All
TOTAL |  |  |  | 13 | 18.5 | 29 | Totals are in man-days.